## Cover Sheet
Annual Delivery Plan Template
Template: ADP 2
June 2023
NHS Board: Healthcare Improvement Scotland

## Annual Delivery Plan 23-24
Recovery Driver Please select from the drop down list: Please note: many of our deliverables contribute to more than one Driver so we have added the columns to the right of the deliverables to indicate this rather than use the drop-down. | SG ADP Action Reference Please select from the drop down list: Please note: many of our deliverables are referenced in multiple ADP1 sections. We have referenced the main sections below but the list is non-exhaustive. Not all references were available in the drop down list so we have updated manually. | NHS Board Deliverable Reference Please create your own reference code for this deliverable | Service Area | Project/Workstream Title | Deliverable Summary Please include a brief summary of the deliverable, briefly outlining the intended action and what this will achieve in 23/24. | ADP1 Primary Care | ADP2 Urgent / Unscheduled Care | APD3 Mental Health | ADP4 Planned Care | ADP5 Cancer | ADP6 Health Inequalities | ADP7 Innovation Adoption | ADP8 Workforce | ADP9 Digital | ADP10 Climate / Environment | Cross-cutting / may contribute to any of the drivers | Q1 Milestones Please outline what you intend to have achieved by Q1 Please note: In our quarterly performance reporting, we will be reporting on planned next steps on a rolling basis so this will be updated throughout the year. | Q2 Milestones Please outline what you intend to have achieved by Q2 | Q3 Milestones Please outline what you intend to have achieved by Q3 | Q4 Milestones Please outline what you intend to have achieved by Q4 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list . | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q1 RAG Status | Progress in Q1 Please outline what you have achieved in Q1 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q2 RAG Status | Progress in Q2 Please outline what you have achieved in Q2 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q3 RAG Status | Progress in Q3 Please outline what you have achieved in Q3 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q4 RAG Status | Progress in Q4 Please outline what you have achieved in Q4 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring.
|  | 1 | COMMUNITY ENGAGEMENT
| 7.3 |  | Cross Organisational | Public Involvement Team | Ensure the work of Healthcare Improvement Scotland is influenced by public views and experience | [6 empty] | X |  |  |  |  | Ongoing support to HIS to improve public engagement through Governance for Engagement Programme, Public Partners and People's Experience Volunteers
| 7.3 | 1.2 | Community Engagement | Participation Network | Research & learning around best practice in community engagement developed, interpreted & shared | [6 empty] | X |  |  |  | X | Monthly webinars held throughout the year (10 in total). 3 webinars to be held in Q1
| 7.3 | 1.2.1 | Community Engagement | Citizens' Panel | 2 Citizens' Panel surveys delivered per year | [6 empty] | X |  |  |  | X | CP11 report to be published in Q1 CP12 report to be published in Q3
| 6.9 | 1.4 | Community Engagement | What Matters To You (WMTY) | Meaningful conversations between providers & users of health & care services promoted & supported | [5 empty] | X |  |  |  |  | X | WMTY Day 2023 undertaken in Q1
| 7.3 | 1.5 | Community Engagement | Community engagement programme | Local people & communities fully involved in decisions about health services; NHS Boards & Integration Authorities supported to continually improve the way they engage with their communities | [5 empty] | X |  |  |  |  | X | Quality Framework launched in Q1 and support will be provided throughout 23/24 to enable NHS boards and health and social care partnerships to use the framework. This will be alongside regular, continuing support to NHS boards and Integration Authorities on best practice in engagement including service change advice.
| 7.3 | 1.5.1 | Community Engagement | Gathering views | Views & experiences of patients, service users, carers & communities gathered & used to shape national policy & practice | X |  |  |  |  | X | X |  |  |  | X | Public views on draft principles for accessing general practice services report published in Q1 Public views on waiting times report published in Q2 Medical implanted devices report published in Q3
| 5.8 | 1.6 | Community Engagement | Service change | NHS Boards & Integration Joint Boards (IJBs) supported on meaningful engagement in relation to service change, options development / appraisal processes, & evaluations | [10 empty] | X | Currently undertaking Quality Assurance of 1 major service change (NHS A&A SACT) and supporting a further 53 service changes.
| 7.3 | 1.7 | Community Engagement | Volunteering in NHS Scotland | NHS Boards supported to develop sustainable volunteering programmes | [11 empty] | Best Practice Guide for Volunteering being developed - publication expected in Q1-2
| 7.3 | 1.7.1 | Community Engagement | Volunteering Information System (VIS) | NHS Boards are better able to manage their volunteers & volunteering programmes | [11 empty] | Work to commence in Q1 on the outline business case for the new system
| 7.3 | 1.8 | Community Engagement | Quality Framework | Launch the Quality Framework for Community Engagement and Participation materials in line with the publication of Planning With People and support roll-out of its use across boards and health and social care partnerships. | [5 empty] | X | X |  |  |  | X | Quality Framework launched in Q1
|  | 2 | EVIDENCE
|  | 2.3 | Data Measurement & Business Intelligence | Core set of indicators | Prepare and review analyses (quarterly) across a set of indicators of quality of care. Highlight notable observations in the data with relevant teams across HIS, to help inform their work. In addition, carry out development work to maximise the beneift HIS gets from these indicators (including refreshing the set of indicators, and also how key observeration on the data are communicated across HIS). | X | X | X | X | X |  |  | X |  |  |  | Q1 milestone - complete quarterly review of the data in May
|  |  |  | Internal intelligence sharing | Redesign the processes and systems used within HIS to gather and share, across HIS' different functions, intelligence about the safety and quality of care. These processes and systems will be redesigned to maximise the benefit that HIS gets from sharing intlliegence across the organisation - while also ensuring HIS provides the necessary input to multiagency intelligence sharing work. | X | X | X | X | X | X |  | X | X |  | X | Present paper/proposals to Executive Team about the development of internal intelligence sharing work
| 7.4 | 2.13 | Scottish Antimicrobial Prescribing Group (SAPG) | Educational Output | Working closely with clinical staff in NHS Boards to promote the safe & effective use of antibiotics across hospital & community settings to tackle antimicrobial resistance | x | x |  | x | [7 empty] | Continue to work in collaboration with NES to create national antimicrobial stewardship framework
| 7.4 |  |  | Guidance | SAPG subgroups have a narrower focus on improving prescribing in an identified area of antimicrobial stewardship. Current groups include : dental, paediatrics & outpatient parenteral therapy | [11 empty] | SAPG OPAT group will continue to expand the medications included in it's good practise prescribing guide for OPAT.
| 7.4 |  |  | QI tools | Work to influence policy & guidance around antimicrobial stewardship at national & international level | [11 empty] | SAPG continues to support creation uk National action plan on AMR.
| 7.4 |  |  | International Partnership with Ghana | Continuation of the antimicrobial stewardship work in Ghana | [5 empty] | x | [5 empty] | Continue working towards agreed project outcomes
|  | 2.15 | Scottish Health Technologies Group (SHTG) | Assessments | Targeted analysis on a health technology, intended to feed into an existing decision - making group within Scotland | x | x | x | x | x | x | x |  |  |  | x
| 7.1 |  |  | Support for Accelerated National Innovation Adoption (ANIA) Pathway | IMTOs published as part of ANIA pathway; provision of scientific advice, HTA for ANIA Value Cases
|  |  |  | Recommendations | Evidence-based SHTG recommendations are developed by a national committee taking into account a range of evidence & stakeholder views
| 6.8 | 2.16 | Scottish Medicines Consortium (SMC) | SMC programme | Provide advice on the clinical & cost effectiveness of new medicines for NHS Scotland. To ensure people in Scotland have timely access to medicines that provide the most benefit based on best available evidence |  |  |  |  | X | X
| 6.8 |  |  | SMC Horizon scanning | Improve financial planning at health board level through the provision of early intelligence on new medicines in development |  |  |  |  | X | X
| 7.4 |  |  | Innovative Licensing & Access Pathway (ILAP) | SMC as a full partner within the Innovative Licensing Access Pathway (ILAP). ILAP connects the medicines regulator with health technology appraisal to create a pathway for early patient access to innovative medicines | [6 empty] | X
|  | 2.42 | Research & Information Service | Rapid Responses | Three tiers of rapid responses ranging from a bibliography to a high level summary of the evidence without critical appraisal. Tier of rapid response guided by need of requester and volume of evidence. | x | x | x |  | x | x | x |  |  |  | x
|  |  |  | Topic Explorations | A high level summary of the available literature on a specific topic or question. Topic explorations help inform SMT's decision in accepting a topic onto the work planner.
| 4.2 | 2.43 | SIGN | Guidelines | Development of evidence-based guidelines, in collaboration with clinicians, other health and social care professionals, patient organisations and individuals. To aid the translation of new knowledge into action | x | x | x | x | x | x | x |  |  |  | x | Melanoma, deteriorating patients guidelines published, perrinatal mood disorders consultation. Chronic paim started
| 4.2 |  |  | Scottish Palliative Care Guidelines | Manage & update Scottish Palliative Care Guidelines in order to ensure a more sustainable & consistent arrangement | [11 empty] | Prioritisation of areass to be updated
| 2.4 |  |  | Scottish Polypharmacy Guidelines | Working in collaboration with SG therapeutics team to update polypharmacy guidelines | [11 empty] | Publication
|  |  |  | 3 Year Scope | Review to consider whether or not published guidelines need to be reviewed after a point of three years | [11 empty] | Asthma completed
|  |  |  | Patient Guidelines | Lay translation of the clinical guidelines. The booklets explain the recommendations in the clinical guideline and help to make patients aware of the treatment they should expect to receive | [11 empty] | Dementia and deteriorating patient started.
|  | 2.44 | Standards & Indicators | Standards | Evidence-informed standards for healthcare (and social care where appropriate) are developed by a national short life working group in consultation with stakeholders | x | x | x | x | x | x |  |  |  |  | x
|  |  |  | Indicators | Evidence-informed indicators for healthcare (and social care where appropriate) are developed by a national short life working group in consultation with stakeholders
|  |  |  | Barnahaus Standard | Development & publication of standards. Expansion of standards link worker model to support children & young people's participation in national governance through involvement in the Pathfinder's selection & the creation of a Children's Charter; provide project support to the Pathfinders project; work with SG & other agencies to develop effective mechanisms for self-assessment, collaborative service design & quality improvement; Provide project support for impact assessments
|  |  |  | Sexual Assault Response Co-Ordination Services (SARCS) | Deliver the requirements as set out in the programme of work to develop & publish refreshed national standards for SARCS & to undertake scoping work in relation to the underpinning Quality Indicators
|  |  |  | National Standards of Care for Adult & Young People's Gender Identity Services | Development & publication of standards of care for gender identity services
|  | 2.45 | Cross Organisational | Global Health QI | QI partnership in Malawi & Zambia | [10 empty] | x
| 7.4 | 2.46 | Research & Information Service | Right Decision Service | Delivery of the right decision support platform at HIS for national scale and adoption | [6 empty] | x |  | x |  |  | Transition into HIS to be complete summer 23
|  | 3 | ihub
| 4.1 | 3.51 | Improving Access | Access QI Collaborative | Work with participanting ENT, Gynaecology amd Urology services to use QI methods to reduce time taken to access care. |  |  |  | x | x | x | [5 empty] | Delivery of in-person Learning Session 4: Testing changes and measuring outcomes. Site visit to each site for coaching support. Data collection from sites. Publication of summary report with key learning to date.
| 1.2 |  |  | Hospital at Home | Support NHS boards and health and social care partnerships to implement or expand Hospital at Home services resulting in a 50% increase in patients managed by hospital at home services by March 2024. |  | x |  |  |  | x | [5 empty] | Learning sessions to spread and share practice improvements. Publication of podcasts and case studies to share learning and good practice. Launch next phase of programmme with a recuitment campaign. Onboard sites to next phase of programme. Deliver in-person Learning Session on identifing areas for improvement. Design process to manage allocation of £3.3million SG funding to H@H services.
| 2.2 | 3.52 | Safety - SPSP Improvement Programmes | SPSP Acute Adult | We will work with strategic partners and NHS boards to deliver the SPSP Acute Adult Collaborative which has a focus on reducing inpatient falls, and early recognition and timely intervention for deteriorating patient | [11 empty] | Deliver 2 in person network meetings Share updated change package, evidence review and resources for falls Conclude Delphi Process for falls. Deliver first Pressure Ulcer network meeting
| 2.8 |  |  | SPSP Perinatal (formerly SPSP Maternity & Children) | We will work with NHS boards and strategic partners to co-design and launch the SPSP perinatal collaborative whch focuses on improving outcomes for women and babies through the reduction of stillbirths, early recognition and response to maternal deterioration, improved experience of caesarean sections and ensuring optimal care for babies. | [11 empty] | Deliver ERG 1 and 2 to support co-design of the driver diagram and change package Test Perinatal Passport with 2 NHS boards Establish data agreement with PHS around Robson Criteria
| 2.8 |  |  | C-Section Improvement Work | Development of a quality improvement programme supporting NHS Boards
| 2.8 |  |  | SPSP Paediatrics (formerly SPSP Maternity & Children) | Working with NHS boards and strategic partners to co-design and launch the SPSP Paediatric Collaborative which focuses on early recognition, timely intervention and person centered mangement of the deteriorating child and young person | [11 empty] | Deliver ERG 1 and 2 to support co-design of the driver diagram and change package
| 2.1 | 3.53 | Frailty Improvement (Cross Directorate) | Frailty Implementation and Improvement Programme | We will design and deliver a new national Frailty Improvement Programme (Focus on Frailty). We will be working with 6 teams (from NHS Boards, health and social care partnerships and GP Practices) to improve the experience of and access to person-centred, coordinated health and social care for people aged 65 and over who are living with frailty or at risk of frailty. We will continue to lead and expand the Frailty Learning System to share practice and promote spread. | x | x | x |  |  | x
| 1.8 | 3.54 | Scottish Patient Safety Programme (Cross Directorate) | Essentials of Safe Care and Learning System | The cross directorate element of SPSP will focus on the following 1. Continuing to embed the Essentials of Safe Care (EoSC) within SPSP programmes of work and wider health and social care sector. This work identifies the key drivers of safe care and is threaded throughout all learning system activity. Resources reflective of support to social care provision and work aligns with SG Healthcare Framework for Adults Living in Care Homes 2. Continued development of the SPSP learning system. Key deliverables being webinar series, facilitation of SPSP/EiC networks, national learning events and publishing of SPSP data and resources to help demonstrate improvement. Focus is also on improving access to SPSP resources and streamlining the way information is presented online. This will help to accelerate learning to support health and social care services to meet the national SPSP aim of improving the safety and reliability of care and reducing harm 3. Development of SPSP logic model. This will support SPSP programme planning, delivery and evaluation. It will bring a standardised approach to reporting and measuring impact across SPSP programmes. 4. Continued collaboration with Excellence in Care. Working collaboratively to offer support to NHS boards to help embed a Quality Management Approach to improvement work. | x | [10 empty] | Q1 Milestones Launch of redeveloped SPSP website pages. Bringing together streamlined SPSP learning system, SPSP resource library and SPSP content from across SPSP programmes SPSP webinar with a focus on EoSC to be held in June 2023. Delivered in collaboration with Care Inspectorate. SPSP/EiC leads network meeting to be held in June 2023 Commence planning for SPSP national learning event which will be held in September 2023 Commence development of SPSP overarching logic model and KPI's to help support standardised approach to measuring impact and outcomes across SPSP programmes
| 1.4 | 3.55 | Community Care and Dementia | Focus on Dementia Improvement Programme | Work with teams across Scotland to support the implementation of key recommendations from the Dementia SIGN Guideline, with a focus on: working with HSCPs/Health and Social Care Teams to improve the quality and experience of post diagnostic support. Leading the Dementia Post Diagnostic Support Network across Scotland. Taking the learning from our Dementia in Hospitals programme to support shared learning into Hospital at Home, SPSP Acute Care Programme and Focus on Frailty programme. Learning Sessions to share and spread practice improvements. | x |  | x |  |  | x
| 3.2 | 3.56 | Mental Health Improvement | Early Intervention Psychosis (EIP) | Continued development and improvement of hub and bespoke EIP services in pathfinder sites to improve outcomes for people experiencing a first episode of psychosis. Gathering and analysis of data to inform implementation progress and understand impact. Delivery of a learning system through national webinars, case studies and communications with national EIP network to increase learning, share insights and keep stakeholders connected with activities of pathfinder sites. Development of a knowledge and skills framework and and online "Essentials of EIP" clinical training module with NES. | x | x | x |  |  | x |  | x |  |  |  | Deliver national EIP network event "Mood disorders and Early Intervention" with guest speaker, end of May. Establish short life working groups to support development of an Implementation Guide for boards and HSCPs looking to design and implement new EIP services. Establish a short life working group to support the EIP learning system. Run in person development day with pathfinder sites at Delta House - 16th May. Run coaching session with pathfinder sites on 29th June. Delivered EIP Expert Reference Group at end of April. Publish case studies (beginning May and end June) Data collection point for pathfinder sites - 19th June Publication of Phase 2 progress report at beginning April
| 3.2 |  |  | SPSP Mental Health | Quality improvement and patient safety programme, specifically developing Patient Safety Climate resources; Essentials of Safe Care; and Scottish Patient Safety Collaborative | x | x | x |  |  | x |  | x |  |  |  | 22 June - SPSPS MH Learning System Webinar "Coercion" 1-1s with Collaborative Teams continuing to understand pressures and where the national team can provide support Weekly drop-in coaching sessions throughout May and June Drop-in session for collaborative tea members focusing on Data with DMBI colleagues - 17 May Set up of MH advisory group - establish membership
| 3.6 |  |  | Personality Disorder | The overall aim of the project is to understand the current state of service provision for people with a diagnosis of a personality disorder, in order to identify the key opportunities for improvement and to then develop proposals to deliver those improvements.
| 1.7 | 3.57 | People Led Care | Designing and Delivering Models of People Led Care (Allied Delivery Programme) | An improvement programme delivering advice, networking opportunities and practical support to health and social care organisations to take a person-centred approach to improving the services they deliver and outcomes for people, families and carers. | x | x | x | x |  | x | x
| 1.7 |  |  | Unpaid Carers Improvement Programme | An improvement programme aiming to ensure that health and care services are designed and delivered to meet the needs of unpaid carers. This includes targetted support to Hospital at Home, Discharge without Delay, quality planning for carers services and for the right to short breaks. | x | x | x | x |  | x |  | x
| 1.7 |  |  | People Led System Transformation: Learning, Engaging Governing | An improvement programme to provide direct support to health and care organisations seeking to implement people led models of care which focus on learning, engaging , governing and ethical commissioning. | x | x | x | x |  | x | x | x
|  |  |  | Coming Home Implementation - Peer Support Network | New commission not confirmed
| 1.1 | 3.58 | Primary Care Improvement | Primary Care Learning System | Host the resilience webinar series in collaboration with the Scottish Government, NHS Education Scotland and the Royal College of General Practitioners (RCGP). Work with people leading and supporting GP Cluster working to share learning that improves the implementation and development of GP Clusters. Work with healthcare professionals implementing Community Treatment and Care (CTAC) services to share learning that improves the delivery of CTAC services. Maintain the Primary Care Quality Improvement Faculty to provide clinical support and leadership for our programmes. Support the delivery of the ihub clinical and professional leadership redesign project (CPLR). Support the delivery of the Improving Together Advisory Group (ITAG). Fund up to three Cluster Quality Leads (CQLs) on the Scottish Quality & Safety Fellowship (SQSF).Programme (subject to additional allocation). Capture learning about the impact of quality improvement in Primary Care. Synthesise and diseminate learnings into tools and resources that enable spread. | x | [10 empty] | Plan and promote Primary Care Resilience Webinar #12. Host one GP Cluster Improvement Network meeting in May 2023. Map and and connect with local cluster leads and create resources to promote the sharing of learning.Facilitate the network MS Teams channel. Support clusters engaged in PCAP. Support one ITAG meeting in May 2023. Lead two CTAC network sessions, in April and June 2023, Publish a CTAC case study on NHS Ayrshire and Arran. Utilise MS Teams and our CTAC mapping resource​ to improve shared learning across the network. Develop an approach to help CTAC teams explore their demand, capacity, activity and queue (DCAQ). Renew contracts with faculty members and continue to engage them in our work. Plan and deliver a workshop to engage key CPLR stakeholders in June 2023, Plan and deliver a workshop to build engagement and collaboratation with Public Health Scotland on Primary Care Improvement in June 2023 Seek opportunities to continue our support of SQSF. Deliver a virtual PCAP Learning Session in April 2023 and a National Sharing the Learning Webinar in May 2023. Publish at least three case studies and a podcast for PCAP.
| 1.1 |  |  | SPSP Primary Care | Scope approaches and initiate work to establish the current safety climate/culture in general practice. Test dedicated improvement sprints for pharmacotherapy to support spread of the serial prescriptions and acute prescribing toolkits. Launch the Quick Guide to Acute Prescribing (short version of the toolkit). Scope opportunities for improvement in the level 2/3 pharmacotherapy space, for example polypharmacy. Ensure all shared SPSP medicines resources are up-to-date, reliable and trustworthy. Further embed medicines safety across all PCIP workstreams. | x | [10 empty] | Refresh stakeholder mapping across Unit A which will contribute to stakeholder analysis for the SPSP Primary Care programme Undertake an option appraisal of safety climate tools for primary care and plan for testing of selected tool/s in quarter 2. Lead the SPSP Excellence in Care Network Meeting in June 2023 with a focus on primary care access. Commence the first dedicated improvement sprints for Pharmacotherapy from May 2023 to support spread of the serial prescriptions and acute prescribing toolkits. ​ Launch the Quick Guide to Acute Prescribing in June 2023.​ Begin to scope opportunities for improvement in the level 2/3 pharmacotherapy space.​ Conclude and publish the NSAIDs evaluation with the University of Strathclyde. Conclude the update of the Sick Day Rules Card. Explore the updated Not Sure Just Ask resource​.
| 1.1 |  |  | Anticipatory Care Planning | Maintain guidance and resources on all aspects of ACP to support health and social care professionals throughout the care planning process. Engage with the Frailty work across the ihub to find opportunities to align our work. Continue to deliver ACP work in line with our available budget and capacity including developing the evidence base for future activities. In 2023-24, this may include: Refreshing website resources.​ Update and republish guidance for using and reviewing eKIS.​ Recruit teams to test approaches to improving the quality of ACP (within eKIS). Collaborating with NES on ACP training resources Collaborating with the Dementia programme to implement the SIGN guideline on Dementia. | x | [10 empty] | Review and replace eKIS resources on the website. Promote current resources and best practice examples including responding to enquiries. Engage with the Frailty and Dementia work across the ihub to find opportunities to align our work. Continue to deliver ACP work in line with our available budget and capacity including developing the evidence base for future activities.
| 1.1 |  |  | Primary Care Improving Access | Deliver, evaluate, and spread the Primary Care Access Programme (PCAP) to support primary care teams to identify the root causes of access issues, prioritise changes and use quality improvement and DCAQ methodology to test and embed changes to improve access to care. | x | [10 empty] | Deliver national cohort 3 until April 2023. Deliver national cohort 4 from May 2023. Develop and test our local scale up and spread plan to franchise delivery of PCAP. Launching inb May 2023 with NHS Lanarkshire and Glasgow City HSCP​. Plan for wider franchising of PCAP to additional boards and HSCPs. Includes developing an off-the-shelf package with all required tools and resources for boards and HSCPs to deliver PCAP locally. ​ Form a national network of local PCAP facilitators Continuinue to share learning through the national lprimary care earning system (see above) and continue to evaluate the impact of the programme with support from EEvIT. Exploring commissioning an external evaluation. Publish a podcast and blog about the PCAP work. Develop comms to be shared in local press.
|  | 3.59 | Quality Management System | We will work with partners to explore, learn and share effective conditions and culture to support Quality Management, Re-design and Improvement to flourish. We have 5 programmes of work which suports the overall aim: QMS NETWORKS: Q UK and QI LEADS QI Connect CQIA Building QI Capacity and capability;NES SLA | For QMS/Creating the Conditions 2023-24 we will: Work with partners (Health Board / HSCP area) to co-design, learn together and prototype an offer to create the conditions, including the culture, capacity and capability for redesign and continuous improvement to flourish. We will do this by: - - scanning the evidence base to review and assess what is known to work - working collaboratively with partners to build relationships and undertake a discovery/diagnostic stage to agree priorities - drawing upon the extensive skills, knowledge, and experience of colleagues both in HIS and the partner organisation/s to work together on progressing these priorities - test improvement offer with 1 NHS Board/Health and Care Partnership - learning together and evaluating impact as the work develops For Q Scotland in 2023-24 we will: · promote Q and engage members to increase membership of the Q Scotland Community · provide a series of opportunities for Q Scotland members to share learning, collaborate and connect in partnership with the Health Foundation. For QI Leads (Peer support and learning network of QI Leads across Scotland) in 2023-24 we will: · co-design and facilitate 4 quarterly meetings with QI Leads to allow opportunities for peer support, connections and shared learning For QI Connect in 2023-24 we will: - research, plan and host 8 global webinars featuring leading thinkers in innovation, improvement, and integration For Continuous Quality Improvement Allocation (CQIA) 2023-24 we will: - review, approve and monitor delivery of NHS Board proposals for the utilisation of CQIA funds focused on improving safety of care and/or redesigning elective care pathways - share learning between NHS Board areas - evaluate the impact of CQIA funds to inform a review and redesign of future purpose of CQIA funds - complete a review and redesign of CQIA For Building QI Capacity and Capability; NES SLA we will: - commission 30 places for Health and Care staff on the Scottish Improvement Leader (ScIL) programme - collaborate with NES to design a QI Capability Building programme for Operational Managers, and test content with one cohort. | [6 empty] | x | x |  |  |  | Develop a case study to be shared on QMS webpages. Begin to develop our compelling story, intentional road map and leadership attitides and behavious to enhance culture and conditions for quality management. Finalise and launch QMS animation Networks: Q UK and QI Leads • Co-design and facilitate one Q Scotland networking event • Distribute one Q Scotland newsletter • Attend one Country partner call with the Health Foundation • Co-design and facilitate one QI Leads meeting QI Connect Deliver scheduled sessions, May and June 2023 Ongoing research, planning and meetings to identify speakers and topics for future sessions CQIA Establish a SLWG to explore opportunities for the redesign of CQIA. Continue to monitor Board CQIA activity offering support to boards where appropriate. Building QI Capacity and Capability; NES SLA Ongoing collabortation with NES colleagues to progress the scoping and development of training offer for operational managers.
[6 empty] | x | x | x | x | x | x | x
[6 empty] | x | x | x | x | x | x | x
[6 empty] | x | x | x | x | x | x | x | x
|  | 3.6 | Strategic Planning | Improving Good Practice in Strategic Planning (Allied Delivery Programme) | A portfolio with four improvement programmes focused on the following areas: • Embed – providing specialist strategic planning input as part of a multidisciplinary transformation team to embed good practice in strategic planning. This includes specialist input to 10 national improvement programmes as well as bespoke support to Scottish Government, HSCPs and NHS Boards. • Create and curate – developing our strategic planning offer including the Good Practice Framework, tools and approaches that can be used by national improvement programmes and local strategic planners in health and social care organisations. • Spread – building strategic planning capacity and capability through prototyping the Strategic Planning Skills Framework, publication of actionable learning insights, development of case studies, and spreading good practice and learning through developing a community of practice. | x | x | x | x |  | x | x | x
| 3.3 | 3.61 | Mental Health and Substance Use (Cross Directorate) | Improving Our Response to People with Mental Health & Substance Use Support Needs in Scotland | Working with pathfinder sites to create integrated and more effective and efficient care and pathways of care for people with concurrent mental health and substance use needs by: Supporting leadership conditions that will ensure sustainability and quaility in implementation; understand local systems and identify changes with local stakeholders; test and implement changes within mulitdisciplinary teams; embed and sustain changes; measure and evaluate impact of changes made; and share findings. | x | x | x | x |  | x | [5 empty] | Pathfinder site activities: NHS Tayside Advisory Group meeting to plan for operational group activities First workshop with mat9operational group - 22 May Further session of leadership development programme to look at "Creating a Recovery Orineted System of Care" - 7 June NHS Lothian Service mapping interviews scheduled with Edinburgh City Council, NHS Lothian and people with lived and living experience of DTTO. Outputs of interviews used at workshop to identify pain points and agree focus areas - 18 May Further workshop in June to plan resources and scope out enablers and barriers. Inverlcyde Two staff conversation events - 2 May online and 18 May in person Delivery group meeting - 23 May Next steps meeting - 16 May Launch event flash report North Lanarkshire Ways of working event - 30 May Delivery group meeting - 24 May Next steps meeting - 3 May Launch event flash report Interconnected systems mapping report Glasgow City Further workshop to be scheduled to review visualisation Visualisation/service map for mild-moderate MH support in substance use services NHS Grampian SLWG meeting around interface document coverage and format - 17 May Review of service visualisation and emerging themes Clinical Network Clinical network advisory group meeting - 31 May Differential diagnosis clinical network event - 20 June Third Sector Commission Start of work under ITQ awarded
| 6.1 | 3.62 | Transformation and Improvement in Drugs and Alcohol and Housing | Medically Assisted Treatment (MAT) Standards Implementation Support | Support the MAT Implementation Support Team (MIST) with the implementation of the MAT standards and support their aim that people with problematic drug use will have timely access to effective care and treatment, with a focus on quality of life and recovery, including : development of national learning system; design of national improvement programme | x | x | x | x |  | x | x | x
| 6.2 |  |  | Pathways to Recovery: Improving pathways into, through and out of residential rehabilitation | To improve referral pathways into and from rehabilitation services, in particular for those with multiple complex needs, so that pathways to residential rehab and aftercare pathways following rehab are clear, consistent and easy to navigate. | x |  | x | x |  | x | x | x
|  |  |  | Embedding Housing in Healthcare (Allied Delivery Programme) | To provide specialist housing input to improvement programmes; focusing on those areas where there would be greatest impact from embedding housing into our work (e.g. those with a focus on home-based delivery of care such as Hospital at Home and Frailty). | x | x |  | x |  | x | x | x
|  | 4 | MEDICAL
| 6.5 | 4.1 | Medicines & Pharmacy | Health & Justice (formerly Prison Pharmacy) | Implementation, monitoring and management of new pharmacy contract. Prison Clinical IT – re-provisioning and Implementation. QA of prison and police custody Safe and Effective use of medicines in custody settings inspection reports U of S Research |  |  | x | x |  | x | [5 empty] | Lead the seamless transition of prison pharmacy services to new provider. Establish mechanisms for ongoing monitoring and management of the contract to deliver continuous improvement in provision. Participate in the review of the contract award process and implement changes identified to ensure improvement. Contribute to the re-provisioning of a prison clinical IT system with appropriate functionalities Define functional requirements, participate in testing and implementation of product Support QAD in undertaking inspection activities in custody settings by undertaking QA reviews of inspections and contributing to the development of standards and indicators for health services in these environments. Through working with National Prison Care Network and ADTCC develop and distribute guidance for the safe and effective use of medicines in prisons. Undertake research activities to test delivery of pharmacy first and pharmacy first plus services to improve self-care options and release medical and nursing time.
|  | 4.2 | Medicines & Pharmacy | Management of Controlled Drugs | Run the Governance Programme and strategic collaboration on improvement in relation to Controlled Drugs. | [11 empty] | Ongoing maintenance and pubication of CDAO register. Supporting CDAO exec meeting 17/5. Annual questionnaire for confirmation of CDAO governance arrangements actioned and actions from responses to be completed close of Q1.
| 6.8 | 4.3 | Medicines & Pharmacy | Area Drugs & Therapeutic Committee Collaboration (ADTCC) | To work collaboratively with NHS boards and Area Drug and Therapeutic Committees to make better use of medicines. | x | x | [9 empty] | ADTCC Forum planned for 24/5. Standing medicines safety items and internal/external medicines information for shared learning across NHS boards ADTCs. Final HEPMA national network meeting undertaken, final information gathering exercise complete and an evaluation report complete. Network membership (56 members / 18 boards) advised topics of interest will be absorbed into ADTCC Forum going forward, due to lack of funding. An initial national network meeting was held, with an attendance of 28 from 14 board areas. The second meeting is planned for late summer 2023. Two active sets of operational guidance on HIS website No National Review Panel submissions received in Q1 as yet
| 6.8 |  |  | HEPMA
National Review Panel (NRP)
| 5.2 | 4.4 | Medicines & Pharmacy | Cancer Medicine (to include OLCM & National Cancer Medicines Advisory Group (NCMAG)) | Continue to provide evidence-based advice on the clinical and cost-effectiveness of cancer medicines outwith the remit of SMC, to improve outcomes for patients plus service efficiency and consistency |  |  |  |  | x
| 5.7 | 4.4.1 | Medicines & Pharmacy | Cancer Medicine (SACT) | Continue to provide clinical leadership and advice on systemic anticancer therapy (SACT) governance within and out-with the organisation |  |  |  |  | x
|  | 5 | NURSING, MIDWIFERY & ALLIED HEALTH PROFESSIONALS (NMAHP)
| 2.2 | 5.1 | Nursing, Midwifery & AHP | Healthcare Staffing Programme | Education & Learning : learning resources published & learning system maintained and updated. Series of training sessions delivered to support launch of real time staffing resources and support to Boards in their preparations for enactment of the Health & Care Staffing Act increased, alongside enhanced support for test Boards | [11 empty] | Progress development of enhanced and expert level learning resources. Plan and deliver training sessions ahead of the launch of the AHP Inpatient Real Time Staffing Resource. Plan and deliver Guidance Chapter webinar series in collaboration with Scottish Government and the Care Inspectorate. Provide training and training resources ahead of the tool runs for all three community tools.
| 2.2 |  |  |  | Workload Tool Development : progress redevelopment of workload tools: maternity, professional judgement, perioperative, mental health & learning disabilities as well as Hospital @ Home workload tool. Support 2 national runs of 3Cs workload tools. | [11 empty] | Establish expert working groups for maternity and mental health and learning disabilities staffing level tools. Agree methodologies for both tools. Action deliverables outlined in the 3C's tool run.
| 2.2 |  |  |  | Work with QAD to provide expertise and educational support on ensuring workforce is incorporated within inspection methodologies and responding to concerns utilising learning to inform future methodology for monitoring of the Health & Care Staffing Act | [11 empty] | Continue to support QAD colleagues with expertise and guidance around workforce planning methodologies for upcoming inspections.
| 2.2 |  |  |  | Real Time Staffing Solutions : series of real time staffing resources developed with NES & launched onto TURAS platform, & working with NSS & Allocate to support the national roll out of e-rostering & the safecare real time staffing system | [11 empty] | Work with NES to develop the AHP Adult Inpatient Real-time Staffing Resource to be launched in June 2023.
| 1.8 | 5.2 | Nursing, Midwifery & AHP | Excellence in Care (EIC) | Continue the EiC Quality measure development and review process ensuring a small suite of measures for nursing and midwifery with consideration to wider MDTs | X | X | X |  |  | X
| 1.8 |  |  |  | Work collaboratively with NES to redesign the 'leading better care' framework into an on-line learning programme on Turas for SCNs / Team Leaders
| 1.8 |  |  |  | Work in alignment with HSP to support integration of EIC Quality and workforce measures to inform appropriate staffing as part of the common staffing method
| 1.8 |  |  |  | Play a key role in progressing digital solutions for quality and care assurance across NHS Scotland
| 1.8 |  |  |  | Strengthen the support to Boards to embedd the EIC framework within their local assurance and governance structures and increase their use of CAIR through increased engagement
|  | 6 | QUALITY ASSURANCE
| 6.5 | 6.25.1 | Inspections | Joint Inspection of Prisoner Healthcare | In partnership with His Majesty's Chief Inspector of Prisons for Scotland (HMIPS) HIS is responsible for inspecting all aspects of healthcare that is delivered in prisons. A full programme of inspections has been scheduled for 2023/24 with the possibility of follow-up inspections when required. Inspection reports outlining the findings from inspections are published on the HMIPS website. |  |  | X |  |  | X
| 2.3 | 6.25.2 | Inspections | Hospital inspections | The aim of this work is to provide assurance of the safe delivery of care in acute hospitals through targeted inspection activity that is reflective of and responsive to the evolving context of service delivery. Inspection of acute hospitals across NHS Scotland results in published reports and NHS board action plans.
| 3.6 | 6.25.3 | Inspections | Joint Inspections of Services for Children & Young People | Joint inspections of community planning partnerships focusing on children and young people at risk of harm delivered in partnership with the Care Inspectorate, Education Scotland and His Majesty’s Inspectorate of Constabulary in Scotland. The intention is to undertake a minimum of three inspections during 2023/24 with published reports outlining what is working well and what needs to improve to ensure that children and young people are safe and protected.
| 3.6 | 6.25.4 | Inspections | Joint Inspections Adult Services | Joint inspections of health and social care partnerships focusing on integration and outcomes delivered jointly with the Care Inspectorate. The intention is to undertake up to three joint inspections during 2023/24 initially focusing on adults with physical disabilities and complex needs and thereafter moving on to a series of inspections with a mental health focused theme. The joint inspections will result in published reports outlining how integration of health and social care is contributing to good outcomes and experiences for these different groups of adults. |  |  | X
| 2.3 | 6.25.5 | Inspections | Adult Support & Protection Inspections (ASP) Inspections Phase 1 | Joint inspections of adult protection partnerships focusing on ASP key processes and leadership of ASP delivered jointly with the Care Inspectorate and His Majesty’s Inspectorate of Constabulary in Scotland. Completion of the final two phase 1 adult support and protection inspections in quarter 1 of 2023-2024. Publication of the final overview report thereafter. The formal Scottish Government commission for phase 2 of the adult support and protection joint inspection programme was received at the beginning of June 2023. Phase 2 will build on, and has been informed by the phase 1 activity and joint inspection key findings. Joint inspection partners are currently in the planning stages in respect of a range of improvement focused inspection and quality assurance activity that will be delivered between August 2023 and July 2025.
| 3.1 | 6.25.6 | Inspections | Mental Health Infection Prevention Control Inspections (Mental Health/ HEI Inspections) | To contribute to the safety and wellbeing of patients and service users within mental health services through the provision of independent assurance. This work will specifically consider infection prevention and control in mental health units. |  |  | X
| 3.6 | 6.25.7 | Inspections | Joint Inspection of Police Custody Suites | Provide expertise to the inspection of healthcare in police custody centres in Scotland led by His Majesty’s Inspectorate of Constabulary for Scotland (HMICS). Inspection reports are published on the HMICS website. |  |  | X |  |  | X
|  | 6.26.1 | Regulation | Regulation of Independent Healthcare (IHC) | As the regulator of registered independent healthcare services in Scotland, we inspect services to ensure that they comply with regulations and meet the required standards of care. Our other regulatory functions include: • registering IHC services • investigating complaints about registered IHC services • managing notifications of IHC registered services • taking enforcement action of registered IHC services where necessary, and • continuing with development work to support the regulation of independent healthcare.
|  | 6.26.2 | Regulation | Ionising Radiation (Medical Exposure) Regulations IR(ME)R | Through inspections and the notifications process, the aim of this work is to ensure public confidence in the safe use of ionising radiation for medical exposure.
|  | 6.27.1 | Reviews | Sharing Intelligence | The Sharing Intelligence Health and Care Group (SIHCG) is undertaking work to review and refresh its purpose and methodology. SIHCG will meet bi-monthly and test a refreshed methodology, from April 2023, with a greater focus on sharing intelligence specifically about emerging concerns about the safety and quality of care.
|  | 6.27.2 | Reviews | Responding to Concerns (RTC) | Ongoing process of assessment and investigation of concerns raised. Work is also being undertaken to refresh the programme. This will focus on making further improvements to the assessment process, our approach to accessing expertise/support and our operational governance processes.
|  | 6.27.3 | Reviews | National Hub for reviewing and learning from child deaths inc. Sudden Unexpected Death in Infancy (SUDI) | Healthcare Improvement Scotland, in collaboration with the Care Inspectorate, co-host the National Hub for Reviewing and Learning from the Deaths of Children and Young People and aim to ensure the death of every child and young person is reviewed to an agreed minimum standard. Through our online portal we receive and quality assure core review data sets from NHS boards and local authorities. We will produce an annual report in Autumn 2023.
|  | 6.27.4 | Reviews | Death Certification Review Service | The Death Certification Review Service (DCRS) provides independent scrutiny of deaths in Scotland not reported to the Procurator Fiscal. Deliverables include ongoing review of approximately 12% of Medical Certificates of Cause of Death (MCCD) and continued support around death certification via the DCRS enquiry line.
|  | 6.27.5 | Reviews | Management of Adverse Events | Support a consistent national approach to identification, review, reporting and learning from adverse events based upon national and international good practice. Deliverables include: Continuation of National Standardisation programme for adverse events reporting. Revision of the Adverse Events Framework in collaboration with the Adverse Events Network group. Further development of the Adverse Events community of practice along with the development of learning systems including learning summary re-design.
|  | 6.27.6 | Reviews | Review of National Screening Programmes | This programme is currently paused to allow for a redesign of the external quality assurance of screening programmes. A business case is in development for the commencement of a test External Quality Assurance of screening programmes, using an intelligence led approach which prioritises areas of risk. |  |  |  |  | X
|  | 6.27.7 | Reviews | External Quality Assurance of Cancer Quality Performance Indicators (QPIs) | This programme is currently paused at the request of Scottish Government to allow for a redesign of the external quality assurance of cancer services. Once the outcome of the redesign is known, we will confirm our planned activity for 2023/24. |  |  |  |  | X
|  | 6.27.8 | Reviews | Cervical Screening Review | Publication of report outlining the review findings and recommendations of the processes, systems and governance for the application and management of exclusions in the Cervical Screening Programme in Scotland | [11 empty] | Report publication. Will complete in Q1 23/24.
| 2.8 | 6.27.9 | Reviews | Neonatal Mortality Review | Undertake an independently chaired review of the processes, systems and governance for delivery of neonatal care in Scotland relevant to the scope of the review. The purpose of the review is to understand any contributing factors to the national increase in neonatal mortality during 2021/22. The scope of this review will cover reported neonatal deaths across Scotland between 1 April 2021 and 31 March 2022. The review report outlining findings and recommendations will be published on the HIS website.
Note on V1: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on AA1: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on AF1: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on AK1: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on AP1: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other